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	1. [bookmark: _Hlk14887621]Description 

	Reference documents / Aconex unique numbers:

	1. Purpose of the Deviation:
Contractors requests Company to aknowledge the change of handrail colour from the originally specified RAL 1016 to RAL 1023, as the handrails have already been painted with RAL 1023. This change is proposed to maintain uniformity and consistency across all modules, ensuring a cohesive appearance throughout the installation.
2. Background and Reason for the Change:
The current Non-Conformity Report (NCR No. 2024-Q-123A90-0004 Rev. 0 here attached) highlights that the handrails were painted with an incorrect RAL colour (1023 instead of 1016) due to misinterpretation of the specifications. 
3. Justification for Acceptance:
· Consistency and Uniformity: The decision to standardize all handrails to RAL 1023 is based on maintaining visual consistency across the entire platform. The selected RAL 1023 has already been applied consistently throughout other areas, including critical modules, ensuring that the overall aesthetic remains uniform.
· Avoiding Project Delays and Additional Costs: Repainting all handrails to meet the original specification would affect the project schedule. The proposed solution mitigates these impact by accepting the current state.
· Safety Considerations Unaffected: The change in colour does not impact the safety, visibility, or functionality of the handrails. RAL 1023 provides sufficient contrast and visibility, meeting safety requirements and ensuring compliance with relevant safety standards.
4. Proposed Actions:
· Accept the use of RAL 1023 as the standard colour for all handrails on the platform.
· Update project documentation and specifications to reflect the new colour standard.
5. Conclusion:
By acknowledging this deviation, we ensure the project maintains visual consistency while avoiding unnecessary rework and possible delays. The adjustment aligns with the broader goal of efficient project management without compromising safety or aesthetic standards.



	2. Response

	Reference documents / Aconex unique numbers


	The Contractor decision to standardise with RAL 1023 on handrails is acknowledged by company. 
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	Reference documents / Aconex unique numbers


	



This communication is issued for the recipient’s information and to facilitate the obligations
of the Parties under the Contract. This communication has no authority to amend                                                                      Page 2/2
or vary the Contract nor relieve either Party of any duties, obligations or responsibilities.								
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